## Project Overview
NIS2 Group Implementation Project
Project Overview
Version 1.0 ¦ Status: Draft ¦ Classification: Internal use ¦ Document owner: Information Security Officer
Field | Value
Project Name | NIS2 Group Implementation Project
Planned Start | 2026-09-21
Planned Completion | 2027-11-30
Project Sponsor | Group Management Board
Project Manager | Information Security Officer
Steering Committee | Management Board; IT Coordinator; Data Protection Officer
Geographic Scope | HQ and all subsidiaries
Regulatory Scope | NIS2 implementation and related national requirements in Germany and the Netherlands
Operational Scope | Governance; risk management; incident handling and reporting; business continuity; supply-chain security; vulnerability management; effectiveness reviews; cyber hygiene and training; cryptography; access control; MFA; secure communications; OT security; compliance evidence
Out of Scope | ISO/IEC 27001 certification and full ISO/IEC 27001 implementation beyond what is required for NIS2
Delivery Model | Part-time project alongside normal operations
Assessment Model | Remote assessments; one full pass over all 174 requirements per entity; partly sequential and partly parallel
Project Team Meeting | Every two weeks
Steering Committee Reporting | Every six weeks and at management gates
Priority Model | High; Medium; Low
Work-Package Principle | Central HQ measures receive priority where they benefit multiple entities
Finding Approval | Findings and recommendations presented by the Information Security Officer to the Management Board
Budget Approval | Information Security Officer for minor expenditure; Management Board for material expenditure
Planning Assumption | Detailed remediation work packages will be created only after the GAP assessments and management approval. Assessment scope was extended from 49 questions to the 161 requirements of the Annex to Implementing Regulation (EU) 2024/2690 plus 13 national requirements; the schedule was re-based on a kick-off in the week of 28 September 2026.
Success Criterion | All applicable NIS2 requirements are implemented, documented and subject to an initial effectiveness review, or remaining risks are formally accepted by authorised management

## Dashboard
NIS2 Group Implementation Project
Project Dashboard
Fully formula-based. Values update as soon as the Master Plan, Work Packages, Gates or Risk records change. No refresh required.
Reporting date
Overall Status |  | Progress by Phase
Indicator | Value | Phase | Activities | Completed | Progress | Overdue
Activities in plan |  | 1. Initiation
Completed |  | 2. Assessment Preparation
In progress |  | 3. GAP Assessments
Blocked |  | 4. Consolidation
Overall progress |  | 5. Remediation
Schedule: Green |  | 6. Verification
Schedule: Amber
Schedule: Red (overdue) |  | Management Gates
Finishing in next 30 days |  | Gate | Planned Date | Status | Days to Gate | Open Activities
Work Packages
Indicator | Value
Work packages defined
Not started
In progress
Completed
High priority open |  | Legend
Overdue (Red) |  | Indicator | Meaning
|  | Green | On schedule or completed
Risks, Issues and Decisions |  | Amber | Planned finish within the next 14 days
Indicator | Value | Red | Planned finish in the past and not completed
Records total |  | Not Planned | No start or finish date entered yet
Open risks
Open issues
High severity, not closed
Escalation needed
Overdue actions
Formulas:
Progress = IF([Activities]="","",[Activities]-TODAY())

## Gantt
NIS2 Group Implementation Project
Gantt Chart (Weekly)
Automatically derived from the Master Plan. Bars follow planned start and finish; the current week is highlighted.
[8 empty] | Oct 26 |  |  |  | Nov 26 |  |  |  |  | Dec 26 |  |  |  | Jan 27 |  |  |  | Feb 27 |  |  |  | Mar 27 |  |  |  |  | Apr 27 |  |  |  | May 27 |  |  |  |  | Jun 27 |  |  |  | Jul 27 |  |  |  | Aug 27 |  |  |  |  | Sep 27 |  |  |  | Oct 27 |  |  |  | Nov 27
ID | Phase | Activity | Start | Finish | Status | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | 2027-04-26 | 2027-05-03 | 2027-05-10 | 2027-05-17 | 2027-05-24 | 2027-05-31 | 2027-06-07 | 2027-06-14 | 2027-06-21 | 2027-06-28 | 2027-07-05 | 2027-07-12 | 2027-07-19 | 2027-07-26 | 2027-08-02 | 2027-08-09 | 2027-08-16 | 2027-08-23 | 2027-08-30 | 2027-09-06 | 2027-09-13 | 2027-09-20 | 2027-09-27 | 2027-10-04 | 2027-10-11 | 2027-10-18 | 2027-10-25 | 2027-11-01 | 2027-11-08 | 2027-11-15 | 2027-11-22 | 2027-11-29

## Master Plan
NIS2 Group Implementation Project
Master Plan
Blue columns are formulas and locked. Gate dates are maintained on the Governance and Gates sheet and pulled in automatically.
ID | Phase | Activity | Primary Owner | Support | Planned Start | Planned Finish | Duration (Weeks) | Dependency | Deliverable / Exit Criterion | Gate | Gate Date | Status | Priority | Progress % | Schedule Status
P1.1 | 1. Initiation | Prepare project kick-off and confirm participants | Information Security Officer | IT Coordinator; DPO | 2026-09-21 | 2026-09-25 |  | None | Kick-off agenda and participant list available |  |  | Not Started | High | 0%
P1.2 | 1. Initiation | Conduct project kick-off | Information Security Officer | All project roles | 2026-09-28 | 2026-10-02 |  | P1.1 | Scope, approach, roles and meeting cadence communicated |  |  | Not Started | High | 0%
P1.3 | 1. Initiation | Confirm project charter, governance and escalation route | Information Security Officer | Management Board; IT Coordinator; DPO | 2026-10-05 | 2026-10-16 |  | P1.2 | Project charter approved | Gate 1 |  | Not Started | High | 0%
P1.4 | 1. Initiation | Confirm assessment method, scope conventions and evidence-request process | Information Security Officer | IT; OT; DPO; advisers | 2026-10-05 | 2026-10-16 |  | P1.2 | Assessment method approved, including the handling of requirements operated centrally at HQ and the evidence-request process | Gate 1 |  | Not Started | High | 0%
P1.5 | 1. Initiation | Confirm assessment benchmark, chapter target levels and scoring model | Information Security Officer | Management Board; IT Coordinator; DE Adviser | 2026-10-05 | 2026-10-16 |  | P1.2 | Management Board confirms Implementing Regulation (EU) 2024/2690 as the applied assessment benchmark; chapter target levels and the scoring model are approved and recorded | Gate 1 |  | Not Started | High | 0%
P2.1 | 2. Assessment Preparation | Populate entity master data, contacts, applicability and central-HQ scope | Information Security Officer | Local Contacts; HR; IT | 2026-10-12 | 2026-10-30 |  | P1.2 | Entity master data maintained in the GAP workbook; requirements operated centrally at HQ pre-scoped for each subsidiary |  |  | Not Started | Medium | 0%
P2.2 | 2. Assessment Preparation | Issue evidence and interview request for every entity | Information Security Officer | Central IT; Local IT; MSP+IT; OT; HR; Procurement; DPO; Advisers; Local Contact | 2026-10-19 | 2026-11-13 |  | P1.4 | Evidence request issued and interview participants confirmed |  |  | Not Started | High | 0%
P3.1 | 3. GAP Assessments | Conduct remote assessment for every entity (174 requirements) | Information Security Officer | Central IT; Local IT; MSP+IT; OT; HR; Procurement; DPO; Advisers; Local Contact | 2026-11-02 | 2027-02-12 |  | P2.2 | Questionnaire completed; initial gaps and evidence recorded |  |  | Not Started | High | 0%
P3.2 | 3. GAP Assessments | Validate findings for every entity | Information Security Officer | Central IT; Local IT; MSP+IT; Advisers | 2026-12-07 | 2027-02-26 |  | P3.1 | Findings factually validated |  |  | Not Started | High | 0%
P4.1 | 4. Consolidation | Consolidate validated findings across all entities | Information Security Officer | IT Coordinator; DPO | 2027-03-01 | 2027-03-19 |  | P3.2 | Consolidated finding register available |  |  | Not Started | High | 0%
P4.2 | 4. Consolidation | Identify common HQ controls and entity-specific gaps | Information Security Officer | Central IT; Local IT; MSP+IT; Advisers | 2027-03-08 | 2027-03-26 |  | P4.1 | Findings grouped into central and local treatment paths |  |  | Not Started | High | 0%
P4.3 | 4. Consolidation | Define proposed work packages and acceptance criteria | Information Security Officer | Work-Package Owners | 2027-03-22 | 2027-04-09 |  | P4.2 | Proposed portfolio with owners and acceptance criteria |  |  | Not Started | High | 0%
P4.4 | 4. Consolidation | Prioritise portfolio using High, Medium and Low ratings | Information Security Officer | IT Coordinator; DPO; Work-Package Owners | 2027-04-06 | 2027-04-16 |  | P4.3 | Prioritised work-package portfolio |  |  | Not Started | High | 0%
P4.5 | 4. Consolidation | Present findings and recommendations to Management Board | Information Security Officer | IT Coordinator; DPO | 2027-04-19 | 2027-04-30 |  | P4.4 | Findings, recommendations and resource needs presented | Gate 2 |  | Not Started | High | 0%
P4.6 | 4. Consolidation | Approve scope, priorities, owners and risk-treatment approach | Management Board | Information Security Officer; IT Coordinator; DPO | 2027-05-03 | 2027-05-14 |  | P4.5 | Approved remediation portfolio and authorised resources | Gate 3 |  | Not Started | High | 0%
P5.1 | 5. Remediation | Launch approved High-priority work packages | Assigned Work-Package Owners | Relevant project roles | 2027-05-17 | 2027-05-28 |  | P4.6 | High-priority packages initiated |  |  | Not Started | High | 0%
P5.2 | 5. Remediation | Implement High-priority and cross-entity HQ measures | Assigned Work-Package Owners | Central IT; Local IT; OT; HR; Procurement; DPO; MSP+IT | 2027-05-24 | 2027-08-31 |  | P5.1 | Approved High-priority measures completed or escalated | Gate 4 |  | Not Started | High | 0%
P5.3 | 5. Remediation | Implement Medium-priority measures | Assigned Work-Package Owners | Relevant project roles | 2027-06-21 | 2027-09-30 |  | P5.1 | Approved Medium-priority measures completed or escalated |  |  | Not Started | Medium | 0%
P5.4 | 5. Remediation | Implement Low-priority measures required for project completion | Assigned Work-Package Owners | Relevant project roles | 2027-07-19 | 2027-10-15 |  | P5.1 | Required Low-priority measures completed, deferred or accepted |  |  | Not Started | Low | 0%
P5.5 | 5. Remediation | Maintain implementation evidence and update GAP responses | Information Security Officer | Work-Package Owners | 2027-05-24 | 2027-10-15 |  | P5.1 | GAP workbook and evidence references kept current |  |  | Not Started | High | 0%
P5.6 | 5. Remediation | Escalate blocked measures and unresolved resource decisions | Information Security Officer | IT Coordinator; DPO; Management Board | 2027-05-24 | 2027-10-15 |  | P5.1 | Material blockers resolved or formally accepted | Gate 5 |  | Not Started | High | 0%
P6.1 | 6. Verification | Review completion evidence against acceptance criteria | Information Security Officer | Work-Package Owners; Advisers | 2027-09-01 | 2027-10-22 |  | P5.2; P5.3 | Evidence reviewed and remaining deficiencies recorded |  |  | Not Started | High | 0%
P6.2 | 6. Verification | Perform proportionate effectiveness checks | Information Security Officer | IT; OT; DPO; MSP+IT; Advisers | 2027-09-27 | 2027-10-29 |  | P6.1 | Effectiveness status updated in GAP workbook |  |  | Not Started | High | 0%
P6.3 | 6. Verification | Obtain formal acceptance of any residual risks | Management Board | Information Security Officer; Risk Owners | 2027-11-01 | 2027-11-12 |  | P6.1; P6.2 | Residual-risk decisions documented | Gate 5 |  | Not Started | High | 0%
P6.4 | 6. Verification | Prepare project closure report and operational handover | Information Security Officer | IT Coordinator; DPO; Work-Package Owners | 2027-11-08 | 2027-11-19 |  | P6.2; P6.3 | Closure report and ongoing control owners confirmed |  |  | Not Started | High | 0%
P6.5 | 6. Verification | Management review and formal project closure | Management Board | Information Security Officer; Steering Committee | 2027-11-22 | 2027-11-30 |  | P6.4 | Project closure approved; remaining activities transferred to operations | Gate 6 |  | Not Started | High | 0%
Formulas:
Schedule Status = IF([Status]="Completed","Green",IF(OR([Planned Start]="",[Planned Finish]=""),"Not Planned",IF(TODAY()>[Planned Finish],"Red",IF(TODAY()+14>[Planned Finish],"Amber","Green"))))

## Work Packages
NIS2 Group Implementation Project
Work Packages
Create work packages only after finding validation and management approval (Gate 3). The WP ID is generated automatically as soon as a work package description is entered.
WP ID | GAP Finding ID | Entity | Measure Area | Work Package | Central or Local | Priority | Owner | Planned Start | Planned Finish | Acceptance Criterion | Expected Evidence | Dependency | Status | Progress % | Schedule Status | Comments

## Governance and Gates
NIS2 Group Implementation Project
Governance, Gates and RACI
Gate dates are maintained here only; the Master Plan reads them automatically.
Gate | Planned Date | Decision | Decision Owner | Required Input | Approval Criterion | Status | Decision Reference | Activities | Open Activities
Gate 1 | 2026-10-16 | Approve project charter, assessment method, benchmark and target levels | Management Board | Scope; roles; schedule; assessment method; applied benchmark; chapter target levels | Scope and responsibilities confirmed; required participants available; benchmark and target levels recorded as a management decision | Not Started
Gate 2 | 2027-04-30 | Accept consolidated GAP findings | Management Board | Validated findings; legal input; cross-entity analysis | Material findings are complete, understandable and supported by evidence | Not Started
Gate 3 | 2027-05-14 | Approve remediation portfolio and resources | Management Board | Proposed work packages; priorities; ownership; resource needs | High-priority and reusable central measures funded and assigned | Not Started
Gate 4 | 2027-08-31 | Review High-priority implementation | Steering Committee | Work-package status; evidence; blockers; overdue actions | High-priority measures completed or supported by approved recovery plans | Not Started
Gate 5 | 2027-11-12 | Accept residual risks and unresolved exceptions | Management Board | Effectiveness results; unresolved gaps; risk recommendations | Residual risks have named owners and documented decisions | Not Started
Gate 6 | 2027-11-30 | Close project and transfer controls to operations | Management Board | Closure report; evidence status; ongoing ownership | NIS2 measures implemented, verified or formally accepted | Not Started
RACI Matrix
Activity | Management Board | Information Security Officer | IT Coordinator | Central IT | Local IT / MSP | DPO | HR | IT Procurement | OT | DE Adviser | NL Adviser
Project charter and scope | A | R | C | I | I | C | I | I | I | C | C
Assessment method | I | A/R | C | C | C | C | I | I | C | C | C
Evidence collection | I | A | C | R | R | R | R | R | R | C | C
Remote assessment interviews | I | A/R | C | R | R | R | C | C | R | C | C
Finding validation | I | A/R | C | R | R | C | I | I | C | C | I
Work-package design | I | A/R | C | R | R | C | C | C | C | C | C
Priority and budget approval | A | R | C | C | C | C | I | I | I | I | I
Technical implementation | I | C | A | R | R | I | I | C | R | I | I
Policy and process implementation | I | A/R | C | C | C | C | C | C | C | C | C
Supplier and MSP measures | I | C | C | C | R | C | I | A/R | I | I | C
Effectiveness review | I | A/R | C | R | R | C | C | C | R | C | C
Residual-risk acceptance | A | R | C | C | C | C | I | I | C | C | C
Project closure | A | R | C | I | I | C | I | I | I | I | I
Role Notes
Role | I I A A: Planning Note
Information Security Officer | I I A A: Overall project manager; prepares findings, recommendations and management decisions
Management Board | I I A A: Sponsor; approves material expenditure, priorities, risk treatment and residual risks
IT Coordinator | I I A A: Steering Committee member; coordinates technical ownership and dependencies
Data Protection Officer | I I A A: Steering Committee member; advises on privacy-related incidents and controls
German External Adviser | I I A A: Specialist support limited to approximately four hours per month
Dutch External Adviser | I I A A: Supports Dutch legal interpretation, entity-specific obligations and finding validation
Central IT | I I A A: Provides controls and evidence for HQ and for the subsidiaries that rely on central IT
MSP | I I A A: Provides controls, evidence and remediation for subsidiaries without internal IT
OT | I I A A: Owns or supports production and industrial-control-system requirements
IT Procurement | I I A A: Supports supplier inventories, contractual requirements and MSP governance
HR | I I A A: Supports personnel security, awareness, onboarding, role changes and offboarding

## Risks Issues Decisions
NIS2 Group Implementation Project
Risks, Issues and Decisions
One record per risk, issue or decision. Due Status is calculated automatically.
Record ID | Type | Date Raised | Description | Impact | Probability | Severity | Owner | Mitigation / Required Action | Target Date | Status | Escalation Needed | Decision / Resolution | Due Status
R1 | Risk | 2026-09-07 | Limited availability because project work is performed alongside normal operations | High | High | High | Information Security Officer | Use phased assessments; restrict meetings; prioritise reusable HQ controls; escalate overdue High-priority tasks | 2026-09-25 | Open | Yes
Formulas:
Due Status = IF(OR([Target Date]="",[Record ID]=""),"",IF(OR([Status]="Closed",[Status]="Accepted"),"Closed",IF(TODAY()>[Target Date],"Overdue",IF(TODAY()+14>[Target Date],"Due soon","On track"))))

## Lists
NIS2 Group Implementation Project
Master Data and Picklists
Single source for all drop-down lists. Add values at the end of a column and extend the named range.
Status | Priority | Phase | Gate | Entity | Owner / Role | Central or Local | Record Type | Rating | RACI | Yes / No | Measure Area | Record Status
Not Started | High | 1. Initiation | Gate 1 | Group / All Entities | Information Security Officer | Central | Risk | High | R | Yes | Governance | Open
In Progress | Medium | 2. Assessment Preparation | Gate 2 |  | Management Board | Local | Issue | Medium | A | No | Risk Management | In Progress
Completed | Low | 3. GAP Assessments | Gate 3 |  | IT Coordinator |  | Decision | Low | C |  | Incident Handling and Reporting | Closed
Blocked |  | 4. Consolidation | Gate 4 |  | Central IT |  |  |  | I |  | Business Continuity | Accepted
Deferred |  | 5. Remediation | Gate 5 |  | Local IT |  |  |  | A/R |  | Supply Chain Security | Escalated
Cancelled |  | 6. Verification | Gate 6 |  | MSP+IT |  |  |  | - |  | Access Control
[5 empty] | Data Protection Officer | [5 empty] | Asset Management
[5 empty] | HR | [5 empty] | Awareness and Training
[5 empty] | IT Procurement | [5 empty] | Cryptography
[5 empty] | OT | [5 empty] | Vulnerability Management
[5 empty] | German External Adviser | [5 empty] | Logging and Monitoring
[5 empty] | Dutch External Adviser | [5 empty] | Physical Security
[5 empty] | Assigned Work-Package Owners | [5 empty] | Supplier and MSP Governance

## Instructions
NIS2 Group Implementation Project
Instructions and Planning Principles
Reference sheet. It contains no project data and does not need to be maintained.
How to Use This Workbook
Sheet | Purpose
Dashboard | Read-only overview. All figures are calculated from the other sheets.
Project Overview | Scope, roles, cadence and success criteria of the project.
Master Plan | The plan of record. Maintain status, priority and progress here.
Gantt | Read-only weekly bar chart derived from the Master Plan.
Work Packages | Remediation backlog. Populated only after Gate 3.
Governance and Gates | Gate dates and decisions, RACI matrix and role notes.
Risks Issues Decisions | Register for risks, issues and management decisions.
Lists | Master data behind every drop-down. Extend here, not in the tables.
Editing Rules
Rule | Explanation
White cells | Input cells. Enter or change values here.
Shaded formula columns | Calculated and protected: Duration, Gate Date, Schedule Status, WP ID, Due Status and every figure on the Dashboard and Gantt sheet.
Sheet protection | Applied without a password. Review > Unprotect Sheet if a formula has to be changed.
Drop-downs | Status, priority, phase, gate, entity, owner and rating values come from the Lists sheet.
Adding rows | Type into the first empty row of a table; formulas and formatting extend automatically.
New picklist values | Add the value at the end of the column on the Lists sheet, then extend the named range under Formulas > Name Manager.
Gate dates | Maintain on the Governance and Gates sheet only. The Master Plan reads them automatically.
Dates | Enter as real dates in the format YYYY-MM-DD, never as text.
Planning Principles
Principle | Application
Keep project management proportionate | Maintain only information required for decisions, ownership, deadlines and escalation
Avoid duplicate records | Detailed findings remain in the GAP Analysis workbook; this workbook references their Finding IDs
Separate assessment from remediation | Do not define detailed remediation work packages before the assessments are complete
Prefer reusable group controls | Prioritise central policies, processes and technical controls that cover several entities
Preserve entity accountability | Each legal entity must confirm local governance, reporting routes, responsibilities and applicability
Use realistic deadlines | Schedule work around operational commitments and limited external-adviser availability
Document decisions | Record scope decisions, risk acceptance, major changes and management approvals
Verify completion | A work package is complete only when its acceptance criterion and expected evidence are available
Work Package Rules
Rule | Instruction
Creation point | Create work packages only after finding validation and management approval
Finding link | Copy the Finding ID from the final GAP Analysis Action Plan
Central or Local | Use Central where one HQ measure covers several entities; otherwise use Local
Priority | Use High, Medium or Low
Acceptance criterion | Describe the observable condition that must be satisfied before closure
Expected evidence | Identify the document, record, report, configuration export or test result required
Closure | Set status to Completed only after evidence has been reviewed
Version 2.0 changes
Assessment scope | The GAP questionnaire now covers the 161 requirements of the Annex to Commission Implementing Regulation (EU) 2024/2690 plus 13 national requirements on incident reporting, registration, management responsibility and OT, for each entity. Assessment windows in phase 3 were extended from three to five weeks per entity.
New activity P1.5 | Gate 1 now also covers the management decision to apply Implementing Regulation (EU) 2024/2690 as the assessment benchmark, and the approval of the chapter target levels and the scoring model.
P1.4 and P2.1 | Extended to cover the scope conventions for requirements operated centrally at HQ and the pre-population of that scope in the GAP workbook before the interviews start.
Schedule | Re-based on a kick-off in the week of 28 September 2026. Planned completion moved from 30 September 2027 to 30 November 2027. Gate dates were shifted accordingly.